Technician Commitment: Renewal Self-Assessment & Action Plan
Executive Summary
Our Stage 3 Technician Commitment submission outlines the University’s continued progress in enhancing the visibility, recognition, career development, and sustainability of our technical staff. Since becoming a signatory of the Technician Commitment in 2018, we have made significant strides in supporting our technical workforce, which remains critical to our success in research, education, and enterprise.
Key achievements include the introduction of a new Level 6 grade within the Technical and Experimental (TAE) job family, providing clearer career progression pathways for technical staff. Additionally, our Career Pathways framework has been refreshed to support staff development and align with sector best practices.
Our 2022-2025 action plan has seen 74% of actions completed, with a further 23% in progress. This demonstrates substantial progress in increasing the visibility and recognition of our technical staff through initiatives such as the Technician Conference and Technician of the Year Awards. Notably, the 2023 Pulse Survey shows that 75% of TAE staff intend to stay at the university for the next two years, marking a 10% increase from 2022.
Governance has been strengthened, ensuring that technical staff are well-represented in decision-making processes through the Technician Commitment Implementation Group (TCIG). This group plays a crucial role in ensuring that the voices of technicians actively shape key institutional policies.
Looking ahead, our 2025-2028 action plan outlines a comprehensive 36-month strategy, with key areas of focus including:
- Visibility and Recognition: Aligning faculty technical lead roles with current needs, ensuring a coordinated approach to communication and engagement, and documenting staff contributions to education and research through frameworks such as REF (Research Excellence Framework), TEF (Teaching Excellence Framework), and KEF (Knowledge Exchange Framework).
- Professional Development and Sustainability: Increasing awareness of the Centre for Higher Education Practice (CHEP) provisions, equipping technicians with grant application skills, enhancing training opportunities, and promoting cross-faculty and cross-Charter collaboration.
- Research Technical Professionals (RTP): Develop a well-defined RTP classification that strengthens RTP research activities, supports career development, and contributes to the university’s research objectives.

This action plan not only aligns with the University’s strategic priorities but also incorporates recommendations from the TALENT Commission, ensuring that our technical community plays a central role in shaping the University’s future growth. In summary, this submission showcases the progress achieved so far and presents a clear vision for how we will continue to develop and support our technical staff in the years ahead.

Organisation: University of Southampton
Name of Institutional Lead: Professor Michael Butler, Dean of Engineering & Physical Sciences
E-mail: feps-dean@soton.ac.uk

Please provide an overview of technical staff structures in your organisation, along with details of any changes since signing the Technician Commitment.
Our technical staff are essential to the success of our research, education, knowledge exchange and enterprise activities. The University is organised into five faculties and a range of professional services functions, supporting a diverse community of over 6,900 staff and more than 25,000 students from around 150 nations. Since becoming a signatory of the Technician Commitment in 2018, we have been working hard to ensure that our technical staff are recognised, supported, and given opportunities for career growth.
This submission focuses on employees in our Technical and Experimental (TAE) job family, which includes 398 members of staff working on our UK campuses. TAE staff represent around 6% of the University’s workforce and are embedded in each of the University’s five faculties (see Figure 1, Figure 2).

Figure 1: Distribution of technicians within the University.

Figure 2: University of Southampton Faculties, Schools and Professional Services functions.
Since joining the Technician Commitment, we have made significant strides in elevating the profile of our technical staff. This is reflected in an upward shift in the grading profile of our TAE population, with a notable increase in the proportion of TAE staff at Level 4 between 2018/19 and 2023/24 (Figure 3 and Figure 4).

Figure 3: Distribution of employees by grade (2018/19; all employees compared with technicians).

Figure 4: Distribution of employees by grade (2023/24; all employees compared with technicians).

Since our last submission in 2021 we have also developed – and are soon set to introduce – a new Level 6 grade within our TAE job family. To date, advancing to Level 6 has required a shift into either our Management, Specialist and Administrative (MSA) job family, or our Education, Research and Enterprise (ERE) job family. As well as acting as a structural barrier to career progression, this arrangement also prioritised management competencies over technical competencies, or required the accumulation of a substantial academic, research or enterprise portfolio. The new TAE Level 6 grade recognises technical expertise in its own right, and that senior technical staff may lead teams or facilities or be highly-specialist individual practitioners.
The creation of TAE Level 6 has been part of a wider refresh of the University’s Career Pathways framework, which includes revised contribution descriptors, updated template job descriptions and refreshed knowledge, experience, and qualification requirements for all existing TAE grades (Level 1b to Level 5). The entire framework refresh, including the introduction of Level 6, was developed in consultation with our Technician Commitment Implementation Group (TCIG) and other stakeholder groups, and draws on sector best practice examples, such as the NTDC National Technician Development Centre (NTDC) Higher Education Technical Taxonomy (HETT) framework. These changes demonstrate our commitment to meaningful career growth for technical staff, and our updated career pathways map, now including TAE Level 6 (Figure 5), will soon be rolled out across the University.

Figure 5: Refreshed Career Pathways map, scheduled for introduction in 2025.

In addition to these enhancements to grading structures and career pathways, we have also begun work to improve job security for technical staff, via our Reducing Casualisation Strategic Major Project, which aims to increase the use of open-ended contracts and streamline the conversion process for fixed-term roles for all University employees. Although the project remains in its early stages, we have begun to see a reduction in the use of fixed-term contracts for technicians (from a long-term average of 32% until 2021/22, down to 27% in 2023/24; see Figure 6).

Figure 6: TAE employees by contract type (2018/19 to 2023/24).

Raised Profiles
The profiles of our technical staff have been raised through successful apprenticeship programmes and career development initiatives (more details in sections 3 and 4). These structured opportunities have allowed technicians to grow within their roles, highlighting the importance of providing opportunities for progression. Efforts driven by TCIG and embedded within our equality charter programme have ensured that technical staff are recognised for their expertise and contributions across the University.

Please provide an overview of the governance, leadership and reporting lines of the Technician Commitment at your institution, along with details on how it is resourced, and information on how your organisation has engaged with the wider community within and beyond your institution. How has this developed since you became a signatory?
Governance, Leadership, and Reporting Lines
Following our commitment as a signatory of the Technician Commitment, we formed a Steering Group in 2019, which has since evolved into the TCIG. The TCIG is responsible for driving actions and ensuring the Technician Commitment remains embedded in the University’s practices. Chaired by the Dean of Engineering and Physical Sciences, who also serves as the Executive Sponsor, the group comprises representatives from each faculty, technical staff, and Human Resources. This structure ensures that technical staff are actively involved in key decision-making processes.
Since our last submission in 2021, we have introduced several governance enhancements. Notably, the Technician Commitment has been integrated into the University’s broader Equality Charters programme, aligning it with other charters such as Athena Swan, the Race Equality Charter, and the Researcher Development Concordat. This alignment has provided additional project management support, creating synergies and efficiencies in action planning.
Additionally, the Communication Working Group has been merged into the Visibility Working Group and the EDI team to streamline efforts in raising awareness of technical staff contributions and increase traffic to the Technician Hub. This merger enhances coordination, especially when the Visibility Group prepares for the annual conference and other communication efforts throughout the year. To further support these initiatives, Associate Deans of Infrastructure have been appointed in the Faculties of Environmental and Life Sciences (FELS) and FoM (Medicine), joining the existing role in Engineering and Physical Sciences (FEPS), ensuring broader representation of technical staff in TCIG meetings.
The governance structure is continually reviewed to ensure it remains fit for purpose. The annual review of the TCIG’s Terms of Reference and membership ensures appropriate representation and confidentiality. Additionally, feedback collection has been improved through action plan management, enabling us to better address the needs of technical teams and align with the remodelling of the TCIG. See Figure 7 for the EDI governance framework.

Figure 7: University EDI governance.

In January 2024, a Co-Chair role was introduced to foster collaboration across faculties, charters, and staff networks. The Co-Chair works closely with Associate Deans of Infrastructure to implement the TALENT Commission’s recommendations and ensure inclusive discussions at TCIG meetings. Technical staff also play a key role in governance through participation in over 20 groups, including EDI Charters and Faculty Boards. This active engagement ensures that the Technician Commitment is embedded in decision-making across the University, promoting inclusive and transparent discussions on issues affecting technical staff. Furthermore, technical staff representation on the University Senate, as noted in Section 4, helps ensure their perspectives are recognised within the wider governance structure, reinforcing the University’s commitment to engaging the technical workforce in shaping institutional policy.

Resources
The TCIG and related activities are well-supported through resources from the EDI team, the Centre for Higher Education Practice (CHEP), and faculty budgets. These resources include funding for 0.2 FTE Technical Leads in three faculties, a 0.5 FTE Equality Charter Project Manager, and centrally funded memberships with the NTDC and HEaTED (Higher Education and Technician Educational Development). HEaTED, which is the training arm of the NTDC, offers Continuing Professional Development (CPD) courses and networking opportunities for technicians across various disciplines and career stages, further supporting their growth and professional development.
In 2024, we secured an additional £10,000 from the UKRI Research England Enhancing Research Culture Fund, which has enabled us to expand initiatives such as the Neurodivergence Acceptance training pilot. This programme raised awareness of neurodivergent staff experiences, and positive feedback has encouraged us to explore further training and job hazard analyses to support neurodivergent staff.
The Research Culture Fund also financed a Conference Representation Pilot, which provided technicians with opportunities to attend national and international conferences, significantly enhancing their visibility and professional networks. This pilot programme saw substantial demand, with 14 applications received in one week and 20 additional queries after the deadline. Due to this high interest, we are exploring ways to expand the programme to accommodate more technicians in the future.

Engagement with the Wider Community
Internally, we actively engage with technical staff through a range of initiatives designed to promote collaboration, recognition, and professional development. The Voice of the Technician Surveys, conducted in 2022 and 2023, have provided valuable insights that inform governance decisions and action plans. Faculty-Specific Forums and Away Days offer opportunities for technical staff to share experiences and collaborate on discipline-specific challenges, while the Senior Technicians Forum, held quarterly, facilitates networking and knowledge sharing among senior technical staff. Since 2022, we have also hosted Technician Conferences and Awards to celebrate technical staff achievements. The 2024 conference, themed "Research Culture and The Southampton University Technical Community," featured workshops on career progression, sustainability, and funding opportunities. Additionally, the Research Culture Roadshow raised awareness of the Technician Commitment and its role in shaping research culture.
Externally, we led initiatives through the Technician Commitment London and South East Technical Network. In July 2024, we hosted a networking event at the Waterfront Campus with colleagues from UCL, Imperial, and others, focusing on technical apprenticeships and career diversity. The event included a tour of RV Callista and demonstrations at the National Oceanography Centre Southampton (NOCS), showcasing technical expertise in marine research.
We are strengthening external collaborations, including a new partnership with Solent University for technician exchanges, which complements our broader initiatives to enhance technical skills development across the sector. As a founding member of the UK Technology Specialists Network (UK TSN), we helped secure a £1.8m ESRC (Economic and Social Research Council) strategic grant. This funding will support new technician development courses starting in October 2024, focusing on essential skills such as grant writing, financing, and outreach. Additionally, the UK TSN, part of the UK Institute for Technical Skills and Strategy, benefits from a £16m national investment aimed at enhancing the skills of technicians who play vital roles in research, ensuring access to bespoke learning and development opportunities across the community.

Please provide a Red, Amber, Green (RAG) analysis on your institutional 36-month action plan indicating which activities you have undertaken and completed (green), which are in progress (amber) and which are still to be carried out (red). Please provide an explanation for those categorised as red. This may be detailed here or attached to this document as an appendix.
Appendix A provides a detailed RAG analysis of the 2022-2025 institutional action plan.

Summary of RAG analysis
Figure 8 shows a summary of our progress. Our action plan consists of 53 actions in total, with 39 actions marked as green (74% action plan completed), 12 as amber (23% in progress), and 2 as superseded (4% still to be carried out/ superseded by new actions).

Figure 8: RAG Summary of Action Plan.

Green Actions
Nearly two-thirds of our actions have been successfully completed, demonstrating significant progress in several key areas:
1. Career Development: Significant progress has been made in career development, including updating recruitment processes (Action 3.1), aligning appraisals with career goals (Action 4.1), and preparing for the introduction of a Level 6 Technical and Experimental role (Action 5.3). Job security has been enhanced by reducing Fixed Term Contracts (FTC) in favour of Open-Ended Contracts (OEC) (Action 5.4), and redeployment opportunities have been promoted to retain expertise (Action 7.5).
2. Sustainability: Efforts have focused on aligning career pathways with apprenticeship standards (Action 8.1), updating the e-recruitment system (Action 8.2), and improving apprenticeship policies (Action 8.3). These initiatives support long-term technical skills and development.
3. Visibility: Technicians' visibility has increased through the launch and enhancement of the Technician’s Hub (Action 11.1), participation in university events (Action 10.3), and successful conferences and events, including the Technician’s Conference (Action 10.2).
4. Recognition: Professional registration for technical staff has been promoted (Action 15.1), with increased participation in the Employer Champion Programme (Action 15.3) and funding secured for development (Action 15.1).

Amber Actions
Around a third of our actions have an amber status. These span various themes such as ‘Recruitment and Induction’, ‘Appraisals and Job Evaluation’, ‘Career Pathways’, ‘Sustainability’, and ‘Apprenticeships’, and represent action areas that are currently in progress. These actions are on track for completion but require longer timeframes due to their alignment with strategic priorities and ambitious programmes of work.

Red Actions
Only two of our 53 actions have not progressed as these have been superseded by new initiatives. Our action to update the generic job description library for TAE roles has been superseded by the wider Career Pathways Refresh (as described in section 1), which will be launched in early 2025. Raising the visibility and recognition of technicians by delivering Manager Briefing documents has been incorporated into Action 12 of our new action plan, reflecting a shift towards more comprehensive and integrated approaches to career development and recognition within the university.
Please provide evidence that your previous action plans are having impact. (For example, you may wish to provide links to initiatives, websites, testimonials, articles/blogs).
We have embedded the Technician Commitment’s key areas— Visibility, Recognition, Career Development and Sustainability—into our broader Equality Charters framework, aligning these goals with the University’s equality, diversity, and inclusion (EDI) priorities (see Figure 9 for the key areas of impact). The key areas of impact within the equality charter programme were chosen by focusing on where positive change can make the most significant difference to both the student and staff experience, particularly in fostering cultural change.

Figure 9: Equality Charters: Key Areas of Impact.

This approach strengthens support for our technical staff across all faculties and professional directorates, ensuring these themes are embedded across the charters and helping us work more efficiently.
The following sections will demonstrate our progress in these four areas— Career Development, Sustainability, Visibility, and Recognition (in the order of our action plan) —and highlight the positive impact our actions have had on the development and support of technical staff.

Career Development
We have made substantial progress in enhancing career development opportunities for technical staff, particularly through our Career Pathway refresh. As noted earlier in this document, this refresh includes the introduction of a Level 6 grade within the TAE job family, which addresses one of the structural barriers to career progression previously experienced by technical staff. Scheduled for full implementation in early 2025, this initiative provides more structured and transparent progression routes, ensuring that senior technical staff can advance without needing to move into management or academic roles. By updating job descriptions and aligning them with apprenticeship standards, this refresh also offers greater clarity and flexibility, a key priority identified in our earlier action plans.
In the past two academic years (2022/23 and 2023/24) we have introduced the option for members of our professional, technical and operation job families (MSA, TAE and CAO) to apply to move into our ERE (Education, Research and Enterprise) job family via our Academic Promotion and Pathway Movement process. While we don’t expect there to be significant flows between these job families, we regard this procedural transparency as an important step in highlighting existing flexibilities and options for career progression. Since this change, four applications have been made to transition from the TAE to ERE job family, primarily to our Knowledge Exchange and Enterprise pathway. All four applications were successful, with two individuals promoted to Level 5 and two to Level 6.
In addition to career progression pathways, we have introduced targeted training initiatives to support the career development of technical staff. Insights from a 2022 skills survey (with a 59% completion rate) helped shape recommendations to the Deans’ Council, directly influencing our Technician Commitment action plan. The findings from the survey helped guide our focus on improving the distribution of training resources and raising awareness of available programmes across faculties. Faculties such as FEPS, FELS, and FoM were allocated training budgets to support development opportunities for technical staff, with a focus on initiatives benefiting multiple technicians. For instance, the School of Biological Sciences used its budget for a team-building visit to the Science Museum for 17 technicians. These initiatives have significantly increased participation in training courses across the institution (see Figure 10).

TAE Staff Attending Training Courses
Figure 10.

Additionally, there has been strong engagement in the Line Manager Development Programme, with 76% of TAE managers starting the course, showing real dedication to leadership development. It is encouraging that 39% of TAE managers have completed the final module. It is also important to note that around 50% of technicians are managed by ERE staff, whose completion rates are lower overall—59% for Module 1. Overall training attendance, including appraisals, the Line Manager Development Programme, and other training initiatives, has improved significantly. Participation increased from 34 in 2022 to 61 in 2023,
Overall, the impact of these initiatives has been positive. Awareness of training opportunities has improved, supported by better communication through SUSSED, faculty channels, and the Technician Hub. The 2023 Staff Pulse Survey highlights increased confidence in accessing training, opportunities for growth, and commitment to remaining at the University. These improvements are clearly reflected in Figure 11 below.

Figure 11: Career Development.

The 2024 Research Culture Landscape Survey pilot, conducted by Vitae (an organisation that supports the professional development of researchers), revealed highly encouraging results, with 70% of TAE staff participating in career development activities. 80% of respondents highlighted strong opportunities for collaboration, while 92% noted clear communication from line managers, and 72% felt supported in terms of mental health. These findings reinforce the positive direction we have been taking with our career development initiatives. We are continuing efforts such as the TAE Career Pathway refresh, which provides clearer progression routes, and targeted training through the Line Manager Development Programme, which equips managers to support their teams more effectively. By expanding networking opportunities and strengthening leadership skills, we are fostering an environment where technical staff can thrive and further develop their careers.
Training feedback has been positive, with staff highlighting the value of workshops, training opportunities, and networking with other technicians. These initiatives have supported both personal and professional development, reinforcing our commitment to meaningful growth opportunities for technical staff.

“I found the session really good... I also enjoyed being with other technicians because we understand each other on a level that we perhaps don’t get with other pathways.”
“The Herschel Programme was inspiring and confidence-building. It has enabled me to develop the soft skills needed to take on more responsibility within my team.”
“The ONI Users group meeting was a great way to connect with others and discuss the successes and challenges of using the Nanoimager. I made useful contacts who will help me get the most out of future super-resolution research projects.”
“Receiving funding for Premiere Pro Colour Grading training built my confidence in a field I did not have direct industry experience in. It allowed me to improve my skills, ask key questions, and make connections that will help me with future video and audio editing challenges.”

### Sustainability
We continue to recognise the importance of apprenticeships as a key strategy for sustaining a skilled technical workforce. Since September 2020, 16 TAE apprenticeships have been initiated, with an average investment of £19,700 per apprentice. Although our 2023/24 apprenticeship intake is lower than preceding years, the commitment to apprenticeships remains strong, as evidenced by ongoing policy and guidance updates. In response to identified needs, we have also expanded the use of apprenticeships for Continued Personal Development (CPD) ensuring that both new and existing staff benefit from development opportunities.
We have consistently worked on refining policies and processes for managing apprentices. In November 2022, we enhanced the recruitment process for apprenticeships with the introduction of a revised E-recruit system, which aligns with institutional procedures and external requirements, such as the Digital Apprenticeship Service. This update has streamlined the identification, agreement, and hiring of apprentices, making the process more efficient and ensuring a sustainable approach to bringing new talent into the technical workforce. In November 2023, an initial draft of refreshed guidance for managing apprentices was shared with TCIG for feedback, with further development planned to support long-term sustainability.

Outreach and Public Engagement for Technical Careers
To further support the long-term sustainability of our technical workforce, we actively engage in outreach and public engagement activities to increase the visibility of technical career opportunities to young people. In FEPS, technicians are key in preparing and executing these events. Their contributions ensure the smooth and safe running of outreach activities, where technical careers, apprenticeships, and work experience placements are promoted to participants. Technicians are often credited for their vital roles in these events, with statements such as, “None of what you have seen today would have been possible without our technical staff.”
Work experience placements, coordinated within FEPS, offer students insight into a variety of technical roles. These placements help break stereotypes about technical careers, allowing students to work directly with technicians. In some cases, students considering degrees in STEM fields work alongside technical staff, gaining valuable hands-on experience in teaching laboratories where technicians design, improve, and implement experiments. In FoM, outreach events such as the New Forest Show, as part of the Wessex Medical Research and PERu (Public Engagement with Research unit) roadshow, further engage local schools and offer students opportunities to learn about the critical work of technical staff.

Supporting Career Flexibility
To further support career sustainability and flexibility, a secondment guidance document was developed in 2023. Ongoing revisions are planned for inclusion on the Technician’s SharePoint site to ensure clarity and accessibility. Additionally, work is underway to establish a new family leave policy that ensures transparency in funding for backfilling long-term absences, helping to maintain operational stability and support during family leave.

Workplace Collaboration, Support, and Satisfaction
A positive and supportive working environment is essential to sustainability, as highlighted by the 2024 Research Culture Landscape Survey pilot. 83% of TAE staff feel supported by their line manager in managing their workload, which is critical for maintaining long-term productivity and preventing burnout. Additionally, 96% of TAE staff feel they have a suitable place to work, with 100% reporting that their working environment is accessible, ensuring that all staff can perform their roles effectively. The survey also revealed that 97% of TAE staff feel physically safe at work, while 72% agree that their working environment supports their mental health and wellbeing. These findings highlight the importance of creating a safe, supportive environment that addresses both physical and mental wellbeing, which are essential components of sustaining a healthy and resilient technical workforce in the long term.
These findings are further supported by the 2023 Staff Pulse Survey (Figure 12), which demonstrates how better use of staff skills and improved resources have contributed to long-term job security and satisfaction among technical staff. These improvements are crucial for ensuring a sustainable and committed workforce.

Figure 12: Sustainability.

These findings reinforce our commitment to providing the necessary resources and opportunities to ensure the sustainability and growth of our technical workforce.

Visibility
We have made substantial progress in raising the visibility of our technical staff across the University through multiple initiatives. A key platform for this has been the Technician’s Hub, launched in 2021, which showcases the work and contributions of technical staff. The Hub has seen steady engagement, with an average of 152 unique viewers per month and a total of 1,824 unique views as of July 2023. It serves as a central resource for training opportunities, events, and technician stories, helping to foster a sense of community and visibility for technical staff.

Visibility has also been strengthened through our Induction Programme. Launched in April 2023 via a centralised SharePoint portal, the induction process ensures that new technical staff are introduced to the Technician’s Hub, making them aware of the available resources and support from day one. The portal provides links to mandatory training and other essential resources, improving engagement with new starters and helping technicians become more visible in the wider University community from the very beginning of their employment.

Externally, visibility has been bolstered through the Technicians at Southampton website and our University of Southampton Technician’s X (formerly Twitter) account (see image below), which has nearly 300 followers and over 400 posts since November 2021. These external platforms have helped celebrate the achievements of technical staff and engage audiences beyond the University, increasing the profile of our technicians in the wider sector.

Our Networking Events have played an important role in increasing technician visibility. For example, in 2023, 65 technicians from across faculties attended a university-wide networking event (photos below), providing a platform to exchange ideas, discuss challenges, and strengthen cross-faculty collaboration. One participant noted: “This networking event was incredibly valuable for connecting with peers across the University. It provided insights into how other teams operate and inspired new approaches that I’ve since implemented in my own work.”
Technicians have also played key roles in university-wide events, further increasing their visibility. During the Science and Engineering Day in March 2023, technical staff hosted a stall that at the event which attracted over 5,000 visitors, showcasing their expertise to a broader audience. Similarly, technicians played a key role in the Winchester School of Art’s Pride T-shirt Design Competition in March 2024, once again highlighting their skills and contributions to both staff and students.
Our annual Technician’s Conference, launched in 2022, has become a key platform for showcasing the work of our technical staff. Attendance has grown from 100 participants in 2022 to 140 in 2024. The format of the conference is planned each year in collaboration with the technical community, allowing it to evolve and accommodate varying preferences, ensuring it remains relevant and engaging for all attendees. The event now includes workshops, developmental sessions and facility tours (2024 photos below).

The Technician’s Conference has also strengthened collaborations across the University, particularly between technicians and other important groups, such as researchers. The co-chair of the Researcher Development Concordat, highlighted these connections, stating,
“The Technician’s Conference was excellent for promoting the range and quality of the work of Technicians and how essential they are to a successful, thriving research culture. It was eye-opening for me to see how many important synergies and overlaps there are in supporting the careers of researchers and technicians.”

This collaboration underscores the alignment between technician roles and broader university goals, including career development and research excellence.
Additionally, results from the 2024 Research Culture Landscape Survey Pilot reinforced the importance of visibility initiatives in fostering a sense of belonging among technical staff. 73% of respondents felt that they are part of a research community at the institution, and 80% reported a strong sense of belonging. These figures reflect the positive impact that visibility initiatives have had on promoting an inclusive research culture at the University.
The 2023 Staff Pulse Survey also highlighted a positive impact on staff morale, with an 8% increase from 2022 in TAE staff agreeing that "people help and support each other here," underscoring the role of visibility initiatives in fostering collaboration.
Through these initiatives—whether at internal events, external platforms like the University’s X account, or ongoing recognition programmes—we continue to raise the visibility of technical staff, ensuring their contributions are recognised and celebrated across the University and beyond.

### Recognition
We actively promote the recognition of our technical staff through both internal and external awards, using the Technician Hub and various communication channels (including our SUSSED news portal and Staff Matters magazine) to encourage nominations and celebrate achievement.
Externally, notable achievements include one of our FoM technicians winning Lab Technician of the Year at the 2023 Lab Awards. Our Chemistry and Chemical Engineering Technical Team were also nominated for the Royal Society of Chemistry Technical Excellence Prize in January 2024, further demonstrating the outstanding contributions of our technical staff.
Internally, technicians have been well-represented and recognised though a range of awards and prizes, including the Vice Chancellor’s Awards, our Technician of the Year Awards and various faculty awards and Deans’ prizes, all demonstrating our commitment to recognising the valuable contributions of technical staff.
Highlights include:
Vice-Chancellor’s Awards: 84 technicians nominated between 2021 and 2024, either individually or as part of teams, with 17 shortlisted and two winning awards.
Technician of the Year Awards: Running alongside our Technician Conference, the Technician of the Year Awards provide an important opportunity to recognise and celebrate the contributions of technical staff. We saw nominations double from 25 in 2022 to 50 in 2023, with 45 in 2024.
FEPS Faculty Awards: 13 technicians were nominated for Faculty Awards between 2022 and 2024, with 12 receiving awards, including two team awards
FELS Dean’s Prize: A Technical Excellence Award category was added to the FELS Dean’s Prize in 2023. Four technicians have since received this award, reflecting the growing recognition of our technical staff’s essential contributions.

Photos from the 2024 Awards can be seen below.

Recognition also extends to daily management practices that ensure fairness and support. The 2024 Research Culture Landscape Survey pilot found that 97% of TAE staff felt their line managers treated them fairly, and 88% felt appropriately supported by their manager. These results underscore the importance of effective management in creating a workplace where technical staff feel valued, which contributes to overall job satisfaction and retention.
We have also developed Fair Attribution Guidance, which works in conjunction with the University’s Authorship, Contribution and Publishing Policy to ensure that technicians are properly acknowledged for their contributions to research through authorship or acknowledgment. Published on the Technician’s Hub and website, this guidance was highlighted by a targeted survey in Spring 2023, revealing that 41% of respondents were aware of it, and 37% had received recognition through it. Between January and September 2024, 49 technicians contributed to 61 publications. Our model of best practice has also been adopted by London South Bank University, further showcasing how we lead in supporting technician recognition.
Representation in Governance has been a key priority for enhancing the recognition and influence of technical staff. A male technical staff representative was elected to the University Senate for a 3-year term in 2021, and in 2024, a female technical staff representative was elected for a term. This reflects our ongoing commitment to ensuring that the voices of technical staff are heard at the highest levels of decision-making. Furthermore, technical staff now participate in over 20 groups across the University, such as EDI Charters and Faculty Boards. This active involvement demonstrates the growing recognition of their expertise and contributions, highlighting the University’s efforts to ensure technical staff are integral to shaping policies and decisions.
Our efforts to enhance recognition and representation have shown clear impact, as evidenced by the 2023 Pulse Survey. The survey revealed a 9% increase in TAE staff agreement with the statement that "their dean or Executive Director makes an effort to listen to their concerns" compared to 2022. This improvement demonstrates that our enhanced leadership structure is fostering better communication and representation of technical staff needs.

Please provide details of how your institution is enacting the recommendations of the TALENT Commission (https://www.mitalent.ac.uk/theTALENTcommission).
In this response, we are highlighting Super Recruiters, EDI Charters, Reducing Casualisation, and Workload Principles, as key examples of institutional work not included in our action plan of how we are enacting the TALENT Commission’s recommendations. These themes align with the TALENT Commission’s focus on inclusive recruitment, diversity, and employment security. Other initiatives relevant to the recommendations, such as apprenticeships, career pathways, and professional development, are already covered in our actions plans, which map out our alignment with the TALENT Commission’s recommendations.

Super Recruiters
One of our most significant initiatives has been the Super Recruiter Project, completed in 2022. This programme developed over 180 trained recruiters, including 12 from the TAE career pathway, who are represented in several faculties. Specifically, FoM has 5 TAE Super Recruiters, FEPS has 4, and FELS has 3. The Super Recruiter initiative aims to ensure that inclusive recruitment practices are embedded across all career pathways, fostering a more diverse technical workforce.
Aligned with the TALENT Commission’s recommendation to support broadening access to technical careers and ensuring inclusive recruitment practices, the University’s Recruiting a Diverse Workforce Checklist—which closely follows the MI TALENT/STEMM-CHANGE guidelines—ensures these recruiters maintain inclusive practices, contributing to a more diverse technical workforce and greater visibility of career pathways.
While some Super Recruiters have had limited opportunities to engage fully in recruitment activities, the training they received has been valuable in improving the quality of recruitment processes they have participated in. Regular recruiters are required to complete Super Recruiter training, helping to ensure inclusive practices in TAE recruitment. Recent updates to university policies, such as changes to the family leave policy, are expected to further enhance inclusive recruitment efforts and attract a more diverse range of candidates for technical roles.

EDI Charters
We are deeply committed to fostering equality, diversity, and inclusion, as demonstrated through key EDI charters such as the institutional Athena Swan Silver Award, Race Equality Charter (Bronze), Disability Confident Leader status, and the University Mental Health Charter (UMHC). Through the Athena Swan Charter, we have implemented targeted actions to support women’s career progression in the TAE pathway. This includes improving Career Pathways guidance to provide clearer routes for development and movement between career pathways, including progression from TAE to other roles. Additionally, we are working to enhance the inclusion of Professional Services staff in gender equality initiatives, extending our efforts beyond traditional academic pathways. Under the Race Equality Charter, the University is focusing on increasing representation and improving career progression opportunities for Black, Asian, and Minority Ethnic (BAME) staff within the TAE pathway. In addition, the Disability Equality Steering Group works closely with the TAE staff network to ensure that staff receive necessary career development support, alongside reasonable adjustments where required. Through the University Mental Health Charter (UMHC), specific initiatives have also been introduced to provide enhanced mental health support for the technical community.

These efforts are aligned with the TALENT Commission’s recommendations to address EDI challenges facing the technical community and ensure the contributions of technical staff are visible and recognised.

Reducing Casualisation
We have taken significant steps to improve job security through a strategic five-year initiative focused on Reducing Casualisation. The goal is to limit the use of casual contracts, ensuring only fully justified fixed-term contracts of less than four years are used, with 15-20% of technical staff transitioning to open-ended (permanent) contracts. This project supports long-term career sustainability and greater integration of technical staff into the University community. This initiative directly supports the TALENT Commission’s recommendation to enhance the sustainability of technical skills and careers, promoting fair employment practices and contributing to a greater sense of job security among technical staff.

Workload Principles
Our Workload Principles, developed for all staff, align with the TALENT Commission’s emphasis on creating supportive and sustainable work environments. Endorsed by the University Executive Board (UEB), these Principles promote balanced workloads and constructive dialogue, with leaders and managers expected to apply them. This commitment enhances our efforts to ensure fair workload management, sustainability, and robust support for technical staff.

Continued Commitment and Embedding Recommendations
We remain committed to working across all relevant EDI Charters and other programmes to ensure the TALENT Commission’s recommendations are fully enacted and embedded in our institutional practices. Through ongoing initiatives like inclusive recruitment, career progression pathways, and job security improvements, we are ensuring that the TALENT Commission’s goals continue to shape the support and development of our technical staff.

Please provide a 36-month action plan; detailing plans to ensure your organisation continues to address the themes of the Technician Commitment and details of how impact will be evidenced and initiatives resourced. This may be detailed here or attached to this document as an appendix.

Appendix B details our action plan for 2025-2028.

For our Action Plan 2025-2028, we have implemented a strategic approach following a Theory of Change Framework. This translates into a more targeted action plan aligned with the broader programme of work, including strategic major projects, and university-wide initiatives such as Equality Charters. We have also diversified the number of business owners contributing to the action plan, including new departments such as CHEP (Centre for Higher Education Practice) and RIS (Research and Innovation Services), and placed a greater focus on cross-collaboration between faculties to build a stronger sense of community and collegiality.

Please evidence how the ‘technician voice’ was present in the development and formation of the 36-month action plan.
The ‘technician voice’ has been central to the development of our Technician Commitment action plan, with a continuous engagement approach ensuring that technical staff influence the plan throughout the three-year period. Every engagement activity—whether through events, training sessions, working groups, or surveys—provides an opportunity for technicians to shape the direction of the plan. Feedback from local activity at the Faculty Level, led by technical leads, is regularly shared with the TCIG and Project Manager, ensuring that the perspectives and needs of technicians are consistently integrated into the action plan’s implementation and development.
 In 2023 and 2024, dedicated on-campus sessions were held to prepare for the new Action Plan, fostering collaboration and collective vision. These sessions were well-attended, with 65 participants at the Networking Day 2023 and 15 attendees at the Senior Technical Forum 2024. These events enabled technical staff to voice their perspectives, share challenges, and provide specific feedback. The insights gathered from these sessions were mapped against the 2022 action plan to identify gaps and areas needing further attention. Feedback from other forums, including the Technician Conference 2024 workshops—attended by over 85 technicians—was also incorporated into the new plan.

From July to October 2024, strategic action planning sessions were conducted with technical leads and business owners, focusing on aligning the ambitions of the Technician Commitment with the University Strategic Programme. These sessions facilitated meaningful dialogue between stakeholders and ensured that the voice of technicians was considered throughout the planning process.

Please confirm that your Technician Commitment status and 3-year action plan is published on your organisation’s website and provide the relevant URL here:
We confirm that our current Technician Commitment status, self-assessment documents and 36 month action plan are published on the University of Southampton Technicians page: https://www.southampton.ac.uk/about/our-people/technical-staff.page
The direct link to the 36-month action plan is: UoS_012025_TC Action plan 2025-2028.odt

Signed: Date: 13th December 2024
Professor Michael Butler
Dean of Physical Sciences and Engineering
Technician Commitment Nominated Institutional Lead

Signed: Date: 13th December 2024
Professor Mark E. Smith CBE
President and Vice-Chancellor
Technician Commitment Signatory – Leader of Institution

Appendix A – RAG review of Action plan 2022-2025
Ref	Theme	Action	Measure	Self- Assessment	RAG	Talent Recommendation
1.1	Self Assessment and data collection: Keep track of the impact of Technician Commitment and progress	Annual survey for TAE staff - "Voice of the Technician" to capture impact, qualitative feedback (start of each new academic year) including feedback on each of the Technician Commitment themes and supported with open feedback sessions.	% take-up of survey improvement year on year 2022 target >30% 2024 target > 40%	2022 response rate 30% 2023 response rate 20% 2024 -Vitae Research Culture Landscape Survey (pilot) response rate 23%. Pulse Survey 65% Network session 2023 (65 participants)	GREEN	Collecting, reporting, and analysing data on the technical workforce Engaging with current and future opportunities
1.2	Self Assessment and data collection: Keep track of the impact of Technician Commitment and progress	Annual data analysis snapshot of technical community to capture; demographics and quantitative information around equality and diversity, recruitment and career progression, and identify any disparities/differences between faculties and locations.	Annual Databook review and workshop, with recommendations collected and fed into university committees as appropriate	Internal EDI Dashboard shared with TCIG. Information included in Self- Assessment.	GREEN	Collecting, reporting, and analysing data on the technical workforce
1.3	Self Assessment and data collection: Keep track of the impact of Technician Commitment and progress	University staff Survey - engagement by TCIG with outputs from staff/pulse surveys, relating specifically to TAE job family; to interpret and support activity relating to key themes and issues raised and feedback to the tech community	% take-up of TAE staff with the UoS survey improves year on year	Participation increased from 57% in PULSE 2 to 65% in PULSE 3. Analysis was shared with TCIG and feedback was received during the self-assessment period.	GREEN	Collecting, reporting, and analysing data on the technical workforce Engaging with current and future opportunities
2.1	TCIG General/Governance: Review governance structures and strategic links to support delivery of action plan	Annual review of Terms of Reference for Technician Commitment Implementation Group (TCIG) and Working Groups; including review of membership to ensure appropriate representation and confidentiality statements returned.	Version control on ToR and membership lists	Membership lists are annually reviewed. Confidentiality agreements were checked in 2022 and 2023. New terms were drafted for TCIG’s remodelling.	GREEN	Ensure the contributions of technical staff are visible and recognised Collecting, reporting, and analysing data on the technical workforce Ensuring technical staff sit on decision-making committees and boards
2.2	TCIG General/Governance: Review governance structures and strategic links to support delivery of action plan	Resource provided by TC role holders reviewed; Faculty Technical Leads (FEPS/FELS/FMED/FAH) (0.2FTE) and Event Coordinator (0.2FTE)	Roles reviewed at appropriate end of term of office	Leads role extended until summer 2025. Event Coordinator role is under review.	AMBER	Ensure the contributions of technical staff are visible and recognised Collecting, reporting, and analysing data on the technical workforce Ensuring technical staff sit on decision-making committees and boards
2.3	TCIG General/Governance: Review governance structures and strategic links to support delivery of action plan	Project Management provided by Equality, Diversity and Inclusion Team to support ongoing links between TCIG and other Charter Marks. Ensure technical staff are represented in each of the other Charter Marks; Athena Swan, Race Equality Charter, Concordat, Disability Confident and Widening Participation.	Project management support is provided TAE representation at each Charter Mark Committee	Project Management provided by Equality, Diversity and Inclusion Team since May 2021. TAE representation in various institutional charters and marks.	GREEN	Inclusion of technical staff within all relevant communication channels and initiatives Address the equality, diversity and inclusion (EDI) challenges facing the technical community
3.1	Recruitment and Induction: Ensure new technical staff are welcomed and brought up to speed with our commitment to our technical community	Promote UoS as a signatory of the TC in recruitment campaigns. Develop standard text for job advertisements (in the body of text) and ensure Technician Commitment logo is visible.	TC visible on all advertisements for TAE staff	Central recruitment processes updated, TC logo now on all TAE staff ads. New standard footer added to TAE ads from January 2024. Inconsistences to be addressed as BAU.	GREEN	Inclusion of technical staff within all relevant communication channels and initiatives
3.2	Recruitment and Induction: Ensure new technical staff are welcomed and brought up to speed with our commitment to our technical community	Induction - Welcome communications from Technicians@soton to new starters, signposting useful info specifically related to TAE staff. New starters identified monthly with support from HR Leadership & Management.	Emails sent from technicians@soton.ac.uk to a monthly circulation list provided by HR	Audit March 2024 - New starters identified monthly, only 3 welcome emails found under the sent folder. Tracking system and automation recommended to improve efficiency.	AMBER	Inclusion of technical staff within all relevant communication channels and initiatives
3.3	Recruitment and Induction: Ensure new technical staff are welcomed and brought up to speed with our commitment	Ensure staff engage with induction programme offered via “Staffbook”. Faculty Induction - develop local induction (Faculty/School/Department), track and monitor completion (also linked to Athena Swan action). Student Introduction - Develop custom and practice of technical staff being introduced to students at the start of all programmes/courses. Consider unique identifier for technical staff working in laboratories, for example, coloured collars/lab coats.	October TC survey to contain a section for new starters from the previous year to receive qualitative feedback and scores. First data to be collected in 2022, with Year-on-Year increases in positive feedback. Lab coat consultation with Technician community and gauge take-up ahead of any implementation	Centralised Induction Portal, launched in April 2023, includes a link to the Technician’s Hub. Each faculty has a local induction page. Coloured collars/lab coats were not something favoured by our technicians.	GREEN	Inclusion of technical expertise in recruitment processes
4.1	Appraisals and job evaluation: Enabling clear career progression, through the provision of regular appraisal conversations with line managers	Support HR in delivering appraisals for all staff: 2021/22 preparations to align Level 1-3 TAE staff appraisals with new system and timeline. 2022/23 - Level 1-3 staff recording first objectives in appraisal system completion rate of >60%. 2023/24 - Level 1-3 first year appraisal completion rate >70%. L4-5 >90% 2024/25 completion rate of >90% for all TAE staff Continue to monitor PPDR reviews and how they are used.	Track and monitor engagement of appraisal and PPDR. > 90% completion rate for all TAE staff by 2024/25	Summary packs with data about completion rates are shared with Deans and HRBPs to detect patterns or trends related to specific staff groups. Data expected in January 2025.	GREEN	Sustainability of technical skills and careers Visibility of clearly defined career pathways and progression routes Supporting career mobility
4.2.1	Appraisals and job evaluation: Enabling clear career progression, through the provision of regular appraisal conversations with line managers	Engage and support Line Managers of Technical staff in the appraisal process and promote a better understanding of the technical pathway and career progression	Manager briefings, communications and engagement plan	Appraisal training available for appraisee, appraiser and 2nd reviewer, guidance on SharePoint and increased communications during appraisal window.	GREEN	Sustainability of technical skills and careers Visibility of clearly defined career pathways and progression routes Supporting career mobility
4.2.2	Career Pathways: Enabling clear career progression, through the provision of regular appraisal conversations with line managers	Engage and support Line Managers of Technical staff in the appraisal process and promote a better understanding of the technical pathway and career progression	Manager briefings, communications, and engagement plan	Engagement and informative sessions in 2023 & 2024 as part of the refreshed Career Pathway project.	AMBER	Sustainability of technical skills and careers Visibility of clearly defined career pathways and progression routes Supporting career mobility Broadening access to technical careers
4.3	Appraisals and job evaluation: Improve guidance and awareness around job evaluations	Increase awareness and transparency around job evaluation process; Develop an e-learning course on job evaluation; Invite Technical leads/Line Manager to attend a job evaluation panels as an observer.	All line managers completed the e-learning course. A decrease in % of staff responding negatively in the survey questions around Career Devt (from 34% to <20%)	In-person workshops delivered in 22,23 & 24 (5 in total). Technical leads couldn’t observe evaluation panels due to confidentiality.	GREEN	Sustainability of technical skills and careers Visibility of clearly defined career pathways and progression routes Supporting career mobility Broadening access to technical careers
5.1	Career Pathways: Improve guidance and awareness around TAE career progression	Update generic job description library for TAE roles from Level 1b to Level 5. Create library of pre-evaluated roles for reference.	Job Description library complete and easily accessible to staff	Superseded by the implementation of the refreshed Career Pathway planned for January 2025 to align with the overall Career Pathway Refresh.
5.2	Career Pathways: Improve guidance and awareness around TAE career progression	Guidance to support career development and movement between different career pathways at Southampton; For technicians this will include greater clarity on how a career at Southampton may move between the Technical and Experimental (TAE) pathway, the Education, Research and Enterprise (ERE) pathway and the Management, Specialist and Administrative (MSA) pathway.	A decrease in % of staff responding negatively in the survey questions around Career Devt (from 34% to <20%) and an increase in # of technical staff visibly moving pathways	Process improved to facilitate mobility across pathways. Over the past two academic years, four individuals successfully moved from TAE to ERE job families, achieving promotions to higher levels. Case studies /guidance underdevelopment.	AMBER	Sustainability of technical skills and careers Visibility of clearly defined career pathways and progression routes Supporting career mobility Broadening access to technical careers
5.3	Career Pathways: Improve guidance and awareness around TAE career progression	Career progression - Consider organisational structure and develop a business case to support the introduction of a Level 6 Technical and Experimental role.	A suitable level 6 TAE role is appointed at the University.	Business Case to support the introduction of a Level 6 Technical and Experimental role approved.	GREEN	Sustainability of technical skills and careers Visibility of clearly defined career pathways and progression routes Supporting career mobility Broadening access to technical careers
5.3.2	Career Pathways: Improve guidance and awareness around TAE career progression	Create TAE Level 6 job description and publicise its availability	A suitable level 6 TAE role is appointed at the University.	Level 6 Technical and Experimental job Implementation of the refreshed Career Pathway planned for January 2025 to align with the overall Career Pathway Refresh.	GREEN	Sustainability of technical skills and careers Visibility of clearly defined career pathways and progression routes Broadening access to technical careers
5.4	Career Pathways: Improve job security and talent retention by reducing the % of TAE staff on Fixed Term Contracts (FTC) and transferring them onto Open Ended Contracts (OEC)	Work in collaboration with the Researcher Concordat working group and Athena Swan teams to build an evidence base and comprehensive understanding of current practice to support next steps. Support with policy reviews and governance updates related to FTC to OEC conversion processes Review all TAE staff currently employed on FTCs with >4 years’ service, with a view to offering those eligible an OEC. We aspire to extend this provision further, contingent on wider university initiatives and policy being implemented.	Any staff with >4 yrs service to have been offered an OEC. A reduction in % of TAE FTC staff is required to successfully complete this action.	Reducing Casualisation Strategic Major Project running from 2023 to 2027	GREEN	Sustainability of technical skills and careers Visibility of clearly defined career pathways and progression routes Supporting career mobility Broadening access to technical careers
6.1	Mentoring: Supporting Continuing Professional Development through mentoring	Develop, support, and encourage mentoring for technical staff; identify those willing to mentor technical staff and those seeking a mentor; at all levels and across the university	A database of technical mentors and mentees. success tracked and monitored through responses to "Voice of Technician Survey".	Mentor recruitment form ready; campaign paused. A database of technical mentors and mentees proposal is being reconsidered. Suggested a pilot scheme with gradual rollout, orientation sessions, and budget support.	AMBER	Sustainability of technical skills and careers Supporting career mobility Engaging with current and future opportunities
6.2	Mentoring: Supporting Continuing Professional Development through mentoring	Work together with the wider university initiatives to ensure that mentoring opportunities for TAE staff are available, visible and promoted by line managers/colleagues.	Technical mentoring accessible via the Technician's Hub. Technical Mentoring resources are signposted from the university mentoring guidance pages. Technical mentoring included in 2 or more good practice examples on the university page.	HR SharePoint site now hosts central resources for mentoring, aiding local programs and mentor communication. Technician’s Hub SharePoint a section on mentoring signposting to central resources. Technician's Hub SharePoint dedicated to mentoring and mentor recruitment form drafted.	GREEN	Sustainability of technical skills and careers Supporting career mobility Engaging with current and future opportunities
7.1	Training and Skills: Ensuring gaps in technical skills are clearly recorded	Southampton Skills survey – leverage our NTDC partnership to conduct a skills survey	Survey launched. Strong engagement >80% per faculty; data analysis complete, new actions created for year 3 and beyond.	Survey completed by 59% staff, Power BI dashboard & data analysed, recommendations presented at Dean’s Council.	GREEN	Sustainability of technical skills and careers Supporting career mobility Ensuring technical contributions are costed appropriately Broadening access to technical careers
7.2	Training and Skills: Promote available training and increase awareness	Review our provision of training for technical staff following the outcome of the Southampton skills survey; technical training, soft skills training, HEaTED, MSLC, leadership and management training. Increase awareness of what is already available and increase visibility of training on the Technician Hub	Year on year increases in % of TAE staff attending training courses.	Limited resource to complete the review. Organic promotion of training already available via Technician's Hub and local networks.	AMBER	Sustainability of technical skills and careers Supporting career mobility Ensuring technical contributions are costed appropriately Broadening access to technical careers
7.3	Training and Skills: Promote available training and increase awareness	Raise awareness of internal training courses; Appraisal, PPDR, Maximising Contribution, Managing Underperformance, effective communications, LMD programme, mental health awareness training.	Year on year increases in % of TAE staff attending training courses.	Distribution of attendance to internal training courses: in 2021 is 20.17% in 2022 is 28.57% In 2023 is 51.26%	GREEN	Sustainability of technical skills and careers Supporting career mobility Ensuring technical contributions are costed appropriately Broadening access to technical careers
7.4	Training and Skills: Reduce barriers to entry for training courses	Improve access to training (by faculty) - clear funding routes and guidance on how to join up for courses.	Year on year increases in % of TAE staff attending training courses.	All faculties, except FAH, have TAE training budgets. They prioritise initiatives benefiting multiple technicians through a call-out system.	GREEN	Sustainability of technical skills and careers Supporting career mobility Ensuring technical contributions are costed appropriately Broadening access to technical careers
7.5	Training and Skills: Redeployment opportunities to improve retention of expertise	Positively promote recently strengthened redeployment policy and associated guidance, with the aim of improving recruiting managers’ perceptions of appointing redeployees.	Increase in # of staff successfully redeploying at the end of FTC.	Policy and guidance are now part of a major strategic project.	AMBER	Sustainability of technical skills and careers Supporting career mobility Ensuring technical contributions are costed appropriately Broadening access to technical careers
8.1	Apprenticeships: Enhancing the apprenticeship process and guidelines	To support the recruitment process of Apprentices; map University grades with apprenticeship levels and National Qualification Framework (NQF) levels and update career pathways guidance accordingly (including work completed by Vis WG to map apprenticeship levels and National Qualification Framework (NQF) to university grades).	Improved recruitment experience for hiring managers (n.b. system updates ready for UAT in November 2021). Guidelines which adapt to changes in the sector, allowing for better leverage of the apprenticeship levy and incentive payments. Reduction in time taken to recruit apprentice, recruitment campaigns aligned with HE timeframes to attract suitable applicants/students into work.	Career Pathways TAE Levels 1b-6 align with apprenticeship standards. Guidance under review.	GREEN	Sustainability of technical skills and careers Broadening access to technical careers Inclusion of technical expertise in recruitment processes
8.2	Apprenticeships: Enhancing the apprenticeship process and guidelines	Update e-recruit system to support current practice; Hiring managers able to raise OSRF at start of process, advertisement on jobs@soton website with links to training provider (for selection process); ensure UoS compliance (UoS recruitment policy, data protection, disability confident etc.); ability to create apprenticeship contract from e-recruit.	Improved recruitment experience for hiring managers (n.b. system updates ready for UAT in November 2021). Guidelines which adapt to changes in the sector, allowing for better leverage of the apprenticeship levy and incentive payments. Reduction in time taken to recruit apprentice, recruitment campaigns aligned with HE timeframes to attract suitable applicants/students into work.	E-recruit system updated in November '22, piloted by technicians. New process aligns with institutional process and Digital Apprenticeship Services.	GREEN	Inclusion of technical expertise in recruitment processes
8.3	Apprenticeships: Ensuring apprenticeship policy is reflective of current practice and supports CPD for staff	Develop a business case for consideration at university level to amend/change the current apprenticeship policy.	Policy which supports sustainability of technical skills through recruitment and continuing professional development. Increased knowledge amongst hiring managers and HR colleagues - no single point of failure in the process Improve morale and opportunities for staff development, particularly for those at lower grades (Levels 1-3 = 55% of TAE staff)	Improved understanding of policy updates needed. Work on new guidance for managing apprentices is ongoing.	AMBER	Sustainability of technical skills and careers Broadening access to technical careers
8.3.1	Apprenticeships: Ensuring apprenticeship policy is reflective of current practice and supports CPD for staff	Engage with key stakeholders and users of the Apprenticeship policy to better understand the challenges and opportunities presented by apprenticeships and clarify the additional resources required to support this work.	Policy which supports sustainability of technical skills through recruitment and continuing professional development. Increased knowledge amongst hiring managers and HR colleagues - no single point of failure in the process Improve morale and opportunities for staff development, particularly for those at lower grades (Levels 1-3 = 55% of TAE staff)	Faculty, HR, and managers attended a process mapping session in December 2022	GREEN	Sustainability of technical skills and careers Broadening access to technical careers
8.3.2	Apprenticeships: Ensuring apprenticeship policy is reflective of current practice and supports CPD for staff	Consider the impact of the Apprenticeship policy for existing staff and include proposals to support the continuing professional development of staff in this review	Policy which supports sustainability of technical skills through recruitment and continuing professional development. Increased knowledge amongst hiring managers and HR colleagues - no single point of failure in the process Improve morale and opportunities for staff development, particularly for those at lower grades (Levels 1-3 = 55% of TAE staff)	Apprenticeships for personal development, are now open to technicians.	GREEN	Sustainability of technical skills and careers Broadening access to technical careers
8.4	Apprenticeships: Sustainability of technical skills for the future (28% of TAE staff are over 50 years, compared to 24% under 30 years; average age 41.7 years)	Faculties (FEPS, FELS, Medicine) to develop annual target for new apprenticeship starters (Gov public sector target 2.3% 2021-2022, although Universities exempt). leverage apprenticeship levy for CPD of current staff	To be financially sustainable should include both apprenticeships from recruitment and CPD. Sustainability working group to track, monitor and analyse impact of apprenticeships at Southampton.	FEPS set and applied a target. Other faculties are now working towards it	AMBER	Sustainability of technical skills and careers Broadening access to technical careers
8.5	Apprenticeships: Engage with National Apprenticeship Scheme, Higher Education and allied partners in apprenticeships for sustainable skills	Engagement with trailblazer schemes and development of apprenticeship standards.	Improved visibility of UoS technical staff externally and at a national level.	Conversation with relevant groups initiated; response was lower than expected. No market for glassblowing.	GREEN	Sustainability of technical skills and careers
9.1	Secondments/ Placements/ Career breaks: Support internal secondments and/or external placement schemes and increase opportunities for CPD	Increase number of secondment opportunities available to all technical community; greater transparency when funding is available to backfill long term absence (ill-health/maternity) or when short-term assignments are availed new responsibilities become available	Increase number of technicians able to engage in short-medium term secondments across faculties.	Exploring solutions for more secondments. New family leave policy planned for 24/25, effective 25/26.	AMBER	Sustainability of technical skills and careers Supporting career mobility Engaging with current and future opportunities
9.2	Secondments/ Placements/ Career breaks: Support internal secondments and/or external placement schemes and increase opportunities for CPD	Develop guidance to support externally funded placements, including long term review of career break policy (2025-26). Build on uptake of schemes akin to the "Changemaker programme" and utilise schemes such as https://careers.smartrecruiters.com/CERN/tte.	Increase number of technicians able to engage with external placements.	Updated Career Break Policy drafted; consultation started. Implementation expected in 2025-2026.	AMBER	Sustainability of technical skills and careers Supporting career mobility Engaging with current and future opportunities
10.1	Events & Comms: Raise the Visibility and Recognition of Technicians and their work across the University	Deliver Manager Briefing documents on how to best recognise the contribution of technicians and improve their visibility, and how to enhance career development and sustainability for the technical community.	Increased nomination numbers for internal and external awards, and improved engagement with appraisal/PPDR process. Monitor on annual basis	Superseded by Action 12 in new action plan.		Sustainability of technical skills and careers Supporting career mobility Engaging with current and future opportunities
10.2	Events & Comms: Raise the Visibility and Recognition of Technicians and their work across the University	Plan and run an annual technician's conference, host a "poster and exhibit" session and invite wider University and students to browse	Conference event + recorded attendance figures. Monitor on annual basis	Technician Conferences from 2022 to 2024 varied in format, including poster exhibits, networking, and panel discussions. Attendance was high, with positive feedback and representation from all faculties.	GREEN	Engaging with current and future opportunities Visibility of technical career pathways and progression routes Supporting outreach and public engagement activities Ensure the contributions of technical staff are visible and recognised
10.3	Events & Comms: Raise the Visibility and Recognition of Technicians and their work across the University	Staff a stall at various annual events e.g. Science and Technology week	Visibility at University events. Monitor on annual basis.	On 16th March, the University’s Science and Engineering Day featured a Technician Stall. The event which attracted over 5,000 visitors. Winchester School of Art hosted a print workshop for Pride T-Shirt Design competitors on 26th March 2024.	GREEN	Engaging with current and future opportunities Visibility of technical career pathways and progression routes Supporting outreach and public engagement activities Ensure the contributions of technical staff are visible and recognised
11.1	Internal Website (HUB): Raise the Visibility of Technicians and their work across the University through use of an internal website / Technicians Hub	Increase internal traffic to the Technician's Hub - maintain and improve content, including information about Technician's Commitment, partnership activities (NTDC), training and Development, events, technician stories - who we are and what we do; SUSSED articles, Staff Matters	Increased traffic to internal site, use google analytics to monitor site usage.	Technician’s Hub, launched in 2021, provides updates and shows increasing viewership. Redesign planned for 24/25	GREEN	Engaging with current and future opportunities Visibility of technical career pathways and progression routes Supporting outreach and public engagement activities Ensure the contributions of technical staff are visible and recognised
11.2	Internal Website (HUB): Raise the Visibility of Technicians and their work across the University through use of an internal website / Technicians Hub	Run workshops and a campaign to encourage technicians to complete a staff profile, (including link to technician commitment and logo, and updated guidance)	Increased numbers of technicians with staff profiles from ~19% to >33% in year 1. ongoing work to encourage new staff to set up profiles and existing staff to maintain and update profile.	From April 2024, TAE staff can add profiles on OneWeb. Faculties are working with IT department to complete the roll out and communications were sent out encouraging TAE to complete Pure profile.	GREEN	Engaging with current and future opportunities Visibility of technical career pathways and progression routes Supporting outreach and public engagement activities Ensure the contributions of technical staff are visible and recognised
11.3	Internal Website (HUB): Raise the Visibility of Technicians and their work across the University through use of an internal website / Technicians Hub	Develop and update internal website to further showcase technicians within the University.	Use Google analytics to monitor site usage and which pages are visited the longest. Aim for 25 unique visits per month, raising to 100 by the end of the action plan due to campaign to raise awareness.	Technician Hub, launched in 2021, has increasing monthly unique views, with peaks during key events and conferences	GREEN	Engaging with current and future opportunities Visibility of technical career pathways and progression routes Supporting outreach and public engagement activities Ensure the contributions of technical staff are visible and recognised
12.1	External Website and networking: Raise the Visibility of Technicians and their work across the University and beyond	Develop and update external website to further showcase technicians and their work to the wider community.	Increased traffic to external site.	Microsite Technicians at Southampton 158 monthly viewers and 1895 unique views since launch in 2022	GREEN	Engaging with current and future opportunities Visibility of technical career pathways and progression routes Supporting outreach and public engagement activities Ensure the contributions of technical staff are visible and recognised
12.2	External Website and networking: Raise the Visibility of Technicians and their work across the University and beyond	Increase external visibility of technicians at Southampton through social media; e.g. LinkedIn, Twitter.	Increased visibility of technicians by individuals and internal comms.	Active Twitter Account since November 2021 - 255 followers.	GREEN	Engaging with current and future opportunities Visibility of technical career pathways and progression routes Supporting outreach and public engagement activities Ensure the contributions of technical staff are visible and recognised
12.3	External Website and networking: Raise the Visibility of Technicians and their work across the University and beyond	Begin contacting local/South Coast universities to start developing a technical network, improving peer to peer visibility of technicians. Continue to support the South-East Technician Forum.	Numbers of Universities sending representatives to network events, development of a branded network. Potential successful funding bids and HEaTED networking day.	Collaboration with several institutes in the South and Southwest, including Southampton Solent University, Bournemouth Arts University, the University of Exeter, the University of Plymouth, University of Bristol and University of West England	GREEN	Engaging with current and future opportunities Visibility of technical career pathways and progression routes Supporting outreach and public engagement activities Ensure the contributions of technical staff are visible and recognised
13.1	Internal and External Recognition through Awards: Raise the Visibility of Technicians and their work across the University through awards and public recognition	Utilise the Technician Hub and comms channels for encouraging external awards and honours nominations; by way of examples; Honorary degrees, Royal Honors System (MBE); British Empire Medal; WISE - new category for technical women; Times Higher Education (THE) Awards - Outstanding technician of the year award; UK Higher Education Technician Summit (HETS Award); Papin prizes (MI Talent), HE Bioscience Technician of the Year, IOP Technician Award, Higher Education Teaching Excellence Award etc. identify potential nominees in advance of nomination windows.	Increase # of nominations celebrate successes of technical staff.	Technician Hub encourages award nominations. Data collection is challenging due to anonymity.	AMBER	Ensure the contributions of technical staff are visible ad recognised Ensure considered inclusion of technical staff within all relevant communication channels and initiatives
13.2	Internal and External Recognition through Awards: Raise the Visibility of Technicians and their work across the University through awards and public recognition	Utilise Technician Hub and comms channels for encouraging internal awards; by way of examples and technician stories; UoS technician of the year award; VC awards; Deans awards; staff achievement awards; technical successes	Increase # of nominations, increase number of articles published about technical staff on SUSSED, Staff Matters, Technician Hub.	Technician Hub promotes internal awards through stories and examples. Various awards open to all staff, some specific to faculties. In 2023, 10 TAE nominations received for VC Awards.	GREEN	Ensure the contributions of technical staff are visible ad recognised Ensure considered inclusion of technical staff within all relevant communication channels and initiatives
13.3	Internal and External Recognition through Awards: Raise the Visibility of Technicians and their work across the University through awards and public recognition	At annual conference; Develop and present a new stand-alone "UoS Technician of the year award" and acknowledge all technical staff who have received an internal or external award.	Staff engaged in nomination process for technician award and annual event.	Technician of the Year awards from 2022 to 2024	GREEN	Ensure the contributions of technical staff are visible ad recognised Ensure considered inclusion of technical staff within all relevant communication channels and initiatives
14.1	Recognising contribution: Technical roles support the University strategic plans for Education, Research, Enterprise.	(Research) Fair Attribution Policy and Guidance developed and published on Technician Hub to support the recognition of contributions made to research by technical staff.	6-monthly report from PURE - Increase number of technicians included in publications.	Fair Attribution Guidance published. https://www.southampton.ac.uk/technicians/technician-commitment/fair-attribution.page#:~:text=Our%20guidance%20document%20works%20in,checklist%20of%20topics%20that%20researchers 2023 internal survey showed low awareness and use of this guidance. London South Bank University adopted the guidance, acknowledging its effectiveness.	GREEN	Ensuring technical contributions are costed appropriately Ensure the contributions of technical staff are visible and recognised Engaging with current and future opportunities
14.2	Recognising contribution: Technical roles support the University strategic plans for Education, Research, Enterprise.	(Education) - Promote the Professional Recognition of Educator Practice (PREP) framework for teaching laboratory roles and those who contribute to the teaching agenda, through workshops, technician stories, appraisal process, technician hub.	Increase number of HEA Fellowships amongst technicians.	CHEP’s PREP workshops for technicians rolling programme. Drop in attendance from 2021 to 2023.	GREEN	Sustainability of technical skills and careers Ensure the contributions of technical staff are visible and recognised Engaging with current and future opportunities
14.3	Recognising contribution: Technical roles support the University strategic plans for Education, Research, Enterprise.	(University wide) - Ensure technical staff are represented at appropriate forums and work together with the relevant teams to ensure representation in the relevant spaces (Staff Engagement Champions and appropriate faculty forums, e.g. Health & Safety committee).	Technical representation on other University Charters and Committees (see also action 2.3).	Effective TAE representation within various governance structures centrally and locally. +D+A49:E50	GREEN	Ensure the contributions of technical staff are visible and recognised Collecting, reporting, and analysing data on the technical workforce Ensuring technical staff sit on decision-making committees and boards
15.1	Professional Registration: To recognise the technical skills of staff through professional registration	Faculty funding to be made available, through annual business planning round, for technical staff to pursue professional registration. Development need identified and time resource, required to be agreed by line manager.	Training budget for professional development included in faculty business plan.	Funding was secured for the Employers Champion Programme, supporting the first five individuals in each faculty	GREEN	Sustainability of technical skills and careers Ensure the contributions of technical staff are visible and recognised Engaging with current and future opportunities
15.2	Professional Registration: To recognise the technical skills of staff through professional registration	Host an annual event on professional registration with Science Council, Engineering Council, and Creative Industries Council, org. writing workshop and/or mentoring event.	Attendance at event and ongoing increase in the number of technical staff pursing professional registration.	Free monthly workshops offered online by the Engineering Council. Support in submission is provided via Employer Champion Programme or Science Council Assessor who is happy to support UoS colleagues. UoS technician mentoring covered under various initiatives and local mentoring schemes.	GREEN
15.3	Professional Registration: To recognise the technical skills of staff through professional registration	Participation in Employer Champion Programme (Science Council) Establish a group who will organise regular workshops supporting professional registration and mentoring (see action 6).	Establish a group who will organise regular workshops supporting professional registration and mentoring (see action 6); increase the number of assessors and staff actively pursuing professional registration	Participation in Employer Champion Programme (Science Council) since 2022.	GREEN	Sustainability of technical skills and careers Ensure the contributions of technical staff are visible and recognised Engaging with current and future opportunities
15.4	Professional Registration: To recognise the technical skills of staff through professional registration	Identify, track and monitor those pursuing and having achieved professional registration; celebrate and recognise these achievements, make them visible on staff profiles (see also action 11.2).	Increase in the number of technical staff pursing professional registration; share success stories; share best practice; encourage those registered to become mentors for others.	The 2023 Voice of the Technician survey - 30% interested in registration, four case studies developed. Limited understanding of voluntary registration numbers, survey anonymous, inconsistencies noted.	GREEN	Sustainability of technical skills and careers Ensure the contributions of technical staff are visible and recognised Engaging with current and future opportunities

Appendix B – Action plan 2025-2028
Ref	Action	Aim	Evidence of Impact	Action owner	Start and End date	Theme	TALENT recommendation
1	Review the Faculty Technical Lead role (FEPS/FELS/FMED/FAH) to ensure it remains relevant, effective, and aligned with organisational strategic objectives at institutional and faculty level.	Aligning the faculty’s technical lead roles with current needs to support the implementation of the Technician Commitment across the University and faculties.	Success of cross-faculty collaboration initiatives (coordinate approach to engagement, mentoring and skill exchange initiatives). Timely delivery of action plan/submission (engagement and TCIG owned actions).	TCIG ADI/Academic Lead Technical Lead	Q1-Q2 2025	Visibility Recognition Career Development Sustainability	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps. Appoint an institutional strategic lead, e.g. Director of Technical Skills, to lead this agenda.
2	Development of the Technician Commitment support role to drive engagement through existing platforms (Hub, Microsite, Inbox, newsletter).	To ensure a coordinated approach to the Technician Commitment communication and engagement activities to support the delivery of our commitment and objectives.	Comms plan with clear metrics attached. Comms plans objectives are met. The Tech Commitment platforms will be updated regularly. Communication resources will be developed.	Sponsor EDI Team	Q1-Q2 2025	Visibility	Ensure considered inclusion of technical staff within all relevant communication channels and initiatives.
3	Develop and implement yearly communication and engagement plan with clear metrics attached to measure impact of the engagement.	To adopt a proactive approach to communication and engagement.	Successful delivery of communication and engagement plan (timeframes and targets) Increased participation in Technician Commitment activities.	HR EDI Team Technician Commitment support role	Q1-Q2 2025	Visibility	Support outreach and public engagement activities regarding technical careers in local schools and colleges to increase visibility of technical career opportunities to young people.
4	Implement a coordinated approach to gathering information from technicians across all faculties and platforms, aligning "Voice of the Technicians" with institutional and local surveys.	To gather comprehensive and consistent data from technicians across all faculties to assess their feedback and improve program effectiveness.	Enhanced decision-making Better resource allocation Action plan effectiveness	TCIG ADI/Academic Lead Technical Lead	Q3-Q4 2025	Visibility Recognition Career Development Sustainability	Be inclusive of technical staff and their considerations in conversations on sector-policy developments. Support technical staff to contribute to and/or attend government events and initiatives to develop policy.
5	Automate the welcome process for new TAE starters to ensure they receive relevant information specific to them about the Technician Commitment and other EDI Charters	To welcome new technical staff and bring them up to speed with our commitment to our technical community.	Visiting rates for the page and opening of the email. New starters questionnaire scores high for TAE staff in the relevant questions. Early engagement with the Hub and relevant activities.	HR EDI Team	Q1-Q2 2025	Sustainability	Ensure considered inclusion of technical staff within all relevant communication channels and initiatives.
6	Promote CHEP’s comprehensive provision to support continuous professional development for technicians ensuring awareness and accessibility of the relevant training and resources.	Increase awareness of CHEP provision among technicians, ensuring CHEP’s comprehensive offer is fully utilised, leading to a more skilled and cohesive technical workforce.	Track career progression of technicians to correlate training and coaching with career advancement.	CHEP	2025 -2027	Career Development	Technical staff should engage positively with current and future opportunities that are available to them
7	Facilitate access to existing Research Funding Development (RFD) resources and supporting structures to enhance technicians’ understanding of the funding landscape and improve their grant application skills.	Equip Technicians with the knowledge and skills needed to effectively identify, apply for, and secure relevant grants.	Increased number of TAE attending grant funding training and accessing RFD resources. Increased number of technical staff submitting grant applications. Positive feedback from technicians on the usefulness of the resources and support provided.	RIS - RFD	2025 -2027	Recognition	Ensure the contributions of technical staff are visible and recognised Enable opportunities for technical staff to be considered as co-investigators, co-supervisors, for grants or projects.
8	Analyse uptake for existing CHEP, HR LMD, and Faculty/School training offers, assess faculty-specific investments, to provide data-driven recommendations for future faculty training allocations.	To enhance the effectiveness and relevance of training and development opportunities for TAE employees.	Increased training uptake Improved performance/progression metrics Reduced turnover rates	TCIG ADI/Academic Lead Technical Lead	Q1 - Q2 2025	Career Development	Technical staff should engage positively with current and future opportunities that are available to them
9	Introduce a framework to enable technicians to create sustainable forums to connect, share best practices, and develop knowledge in specific areas of their professional practice.	To equip technicians with the necessary tools and techniques to form effective knowledge sharing and collaboration systems.	Informative sessions attendance numbers. Areas of Interest and volunteers identified. Self-managed forums are in place. Feedback from identified participants.	TCIG CHEP	Q3 2025 - 2027	Career Development Sustainability	Strategic approach to ensure the sustainability and appropriateness of technical skills and careers, at both a local and national level (Training and development)
10	Identify mentors at all levels across the university and collaborate with local initiatives (faculties and schools) to ensure visibility and promote mentoring for technical staff.	To align with existing mentoring initiatives to maximise resources available while offering suitable mentoring opportunities to technical staff.	Increase in the number of mentors Mentoring programmes available to technical staff. Feedback from identified mentees & mentors.	ADI & Faculty Academic Leads	Q3 2025	Career Development Sustainability	Strategic approach to ensure the sustainability and appropriateness of technical skills and careers, at both a local and national level (Training and development)
11	Integrate TAE in the UoS Talent Plan rollout across all faculties, including overhauling the Super Recruiter (SR) program, as outlined in the “University of Southampton Talent Plan Strategy" 2024-2030.	Implement the University of Southampton Talent Action Plan across the TAE job family to attract, develop, retain, and maintain a diverse and high-performing workforce.	Successful roll out of succession planning across TAE. Increase in the number of quality candidates applying for positions at the University of Southampton. TAE participation in Super recruitment programme. Positive feedback from candidates regarding the recruitment process. Increase in employee satisfaction and engagement scores related to learning and development opportunities. Improvement in performance metrics attributed to employee skill enhancement and development efforts. Build confidence of our Leaders and Managers to effectively manage both high performing staff and staff who require development. Retain: Tracking of areas of high turnover, with underpinning investigation into why they exist. Tracking of Internal/ external applicants for opportunities. Positive feedback from employees regarding workplace culture, recognition, and opportunities.	HR Talent & Resourcing HR LMD HRBPs	2024 -2030	Career Development Sustainability	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps.
12	Promote line management tools to support the effective management of TAE staff, recognising the unique responsibilities and expectations of TAE roles compared to other job families.	Enhance the management of TAE staff by raising awareness of line management tools.	Improvement in the quality of appraisals for TAE staff. Improvement in scores of key indicators for TAE staff (job satisfaction, retention rates, progression, recognition, and progression).	HR LMD	Q3 2025 Q3 2026 Q3 2027	Career Development	Ensure provision and protected time for training and professional development, supporting technical staff to take advantage of development opportunities, such as technical training, placements, and/or professional registration. Define a minimum yearly allowance of days for technical staff to undertake professional development.
13	Review how TAE staff are engaging with the new "unpaid career breaks" policy to understand how technicians are using it to engage in professional development opportunities.	Foster a culture of continuous learning and professional development among TAE staff at the UoS, while also ensuring the university’s operational efficiency and effectiveness.	Number of TAE eligible employees taking career breaks for personal development. Acquisition of skills or certifications obtained by employees during their breaks. Increased employee satisfaction.	HR R&R	2026 - 2028	Career Development	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps.
14	Implement a skills exchange programme to provide opportunities for learning and development (job shadowing, job swap, or similar) for TAE.	Foster a culture of continuous learning and professional development among TAE staff at the UoS, while also ensuring the university’s operational efficiency and effectiveness.	Increased number of opportunities Job satisfaction Retention Strengthen links with other departments and institutions (joint projects/collaboration).	TCIG HRBP	2025 -2028	Career Development Sustainability	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps. Ensure provision and protected time for training and professional development, supporting technical staff to take advantage of development opportunities, such as technical training, placements, and/or professional registration. Define a minimum yearly allowance of days for technical staff to undertake professional development.
15	Rewrite the apprenticeship guidance to address current gaps and inefficiencies in the guidance and to further align with organisational goals.	To improve apprenticeship outcomes and the support of workforce development by aligning with evolving organisational goals.	Improved feedback from hiring managers.	HR R&R	2025 -2026	Sustainability	Expand entry routes to technical roles and careers by encouraging applicants from both vocational pathways and academic pathways Invest in apprentices and trainee technician positions, hosting placements for qualifications (e.g. T-Levels in England) and work experience placements for local schools and colleges. Utilise the Apprenticeship Levy for training and developing technical staff.
16	Socialise the re-written TAE job family and guidance following the introduction of a TAE L6 Grade and the completion of the Career Pathway Refresh Project.	To inform stakeholders and help them understand the new TAE L6 Job Description and the refreshed Career Pathway to improve role clarity, career development opportunities, and career progression routes.	Changes on the distribution of employees by grade (flatten distribution - Number of TAE L6 roles). Improved progression rates across the board. Sustained job satisfaction indicators. Improved score at Research Culture Survey Pilot (or similar indicator).	HR R&R HRBP	2025 -2026	Recognition	Visibility of clearly defined career pathways and progression routes, with accurate and standardised job descriptions for technical roles. Support the development and implementation of a new, simple, and fit-for purpose classification for technical roles in higher education, research, and innovation at all levels, such as by creating a new job family specifically for technical roles, separate from academic, administrative, or any other job family.
17	Document the positive impact on visibility, research culture, policy implementation, and collaboration of having technician representation on institutional and faculty committees.	To increase TAE visibility and recognition by evidencing the positive impact of having technician representation on institutional and faculty committees.	Success of cross-faculty collaboration initiatives. Instances where technician input significantly influenced committee outcomes.	TCIG ADI/Academic Lead Technical Lead	2025 - 2027	Recognition	Ensure representation of technical staff on department-, faculty-, and institution-level decision-making committees, boards, panels, and similar groups, through either a dedicated seat or designated technical advocates within senior leadership and/or existing members. This includes processes and committees to develop institution-wide strategies and long-term goals.
18	Develop a standardised process to ensure the contributions Technicians make to teaching and supporting students are considered when completing the TEF return for the university.	To ensure technical staff are appropriately recognised for their contribution to education.	Technicians are explicitly mentioned in TEF	TEF development team	2026 -2029	Recognition	Review how staff contributions are recognised and rewarded at department- and institution-level, and whether inclusivity exists across all job families.
19	Design and implement a process to document the contributions of technicians to research at institutional and unit of assessment level.	To ensure technical staff are appropriately recognised for their contribution to research.	Increased number of publications acknowledging technicians’ contributions recorded. Technicians are explicitly mentioned in REF.	RIS Library	2026 - 2029	Recognition	Review how staff contributions are recognised and rewarded at department- and institution-level, and whether inclusivity exists across all job families. Encourage appropriate inclusion of technical staff as authors, co-authors, or contributors on published papers and presentations.
20	Develop a programme of work supporting technicians to deepen their understanding in research integrity and trusted research awareness through structured and collaborative efforts.	To enhance technicians understanding of research integrity and trusted research topics, while enabling them to participate in shaping key policies through structured and collaborative initiatives.	Participation on awareness and training sessions. Contribution and policy feedback participation. Success stories technicians apply learned best practices in their research activities. Improvement on Research Culture Survey score (TBC).	RICO	2025 - 2028	Career Development Visibility	Ensure representation of technical staff on department-, faculty-, and institution-level decision-making committees, boards, panels, and similar groups, through either a dedicated seat or designated technical advocates within senior leadership and/or existing members. This includes processes and committees to develop institution-wide strategies and long-term goals.
21	Establish a collaborative partnership between the Researcher Development Concordat & Technician Commitment to address the shared goals of promoting professional development and ensuring recognition and inclusion both groups.	To enhance the collaboration between the Researcher Development Concordat and the Technician Commitment, creating a holistic approach to research culture that fosters a supportive and inclusive environment.	Growing changes influenced by joint advocacy. Increase of collaborative projects and initiatives launched. More frequent joint meetings and workshops. A greater number of cross-functional training sessions conducted. Surging joint publications and research outputs.	RDC TCIG	2025 - 2028	Visibility Recognition Career Development Sustainability	Ensure representation of technical staff on department-, faculty-, and institution-level decision-making committees, boards, panels, and similar groups, through either a dedicated seat or designated technical advocates within senior leadership and/or existing members. This includes processes and committees to develop institution-wide strategies and long-term goals.
22	Engage with TAE staff and the TCIG, ensuring the voices of technicians are heard and their recommendations integrated into the Reducing Casualisation project’s framework.	To reduce casualisation at the University of Southampton, thereby enhancing job security, promoting fair employment practices, and making the University an employer of choice.	A reduction in % of TAE FTC staff. Improved uptake of redeployment opportunities. Lower staff turnover and higher talent retention. Improvement in survey scores and engagement.	Reducing Casualisation Project	2024-2028	Career Development Sustainability	Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps.
23	Investigate and analyse the approaches taken by other institutions in relation to Research Technical Professionals.	To understand the role and recognition of Research Technical Professionals in other institutions, and how this may inform usage of Southampton's current job families and career pathways.	Conduct a Russell Group desk review and engage with representatives from different institutions. Gather insights and best practices from each institution. Set of clear, actionable recommendations.	HR R&R TCIG	2025 - 2027	Career Development Sustainability	Enable opportunities for technical staff to be considered as co-investigators, co-supervisors, for grants or projects. Support the development and implementation of a new, simple, and fit-for purpose classification for technical roles in higher education, research, and innovation at all levels.
24	Identify and understand the extent our Research Technicians Professionals (RTPs) cohort to inform decision-making and ensure existing recognition mechanisms are effective, equitable, and aligned with career development pathways.	A well-defined RTP classification that strengthens RTP research activities, supports career development, and contributes to the university’s research objectives.	Evidence-base decision making / informed decision. Improved employee satisfaction indicators.	HR R&R TCIG	2025 - 2027	Career Development Sustainability	Enable opportunities for technical staff to be considered as co-investigators, co-supervisors, for grants or projects. Support the development and implementation of a new, simple, and fit-for purpose classification for technical roles in higher education, research, and innovation at all levels.

Abbreviations
ADI	Associate Dean Infrastructure
CHEP	Centre for Higher Education Practice
EDI	Equality Diversity and Inclusion
FAH	Faculty of Arts and Humanities
FELS	Faculty of Environmental and Life Sciences
FEPS	Faculty of Engineering and Physical Sciences
HR	Human Resources
HRBP	Human Resources Business Partner
LMD	Leadership and Management Development
MED	Faculty of Medicine
R&R	Reward and Recognition
REF	Research Excellence Framework
RFD	Research Funding Development
RICO	Research Integrity and Compliance Office
SR	Super Recruiter
TAE	Technical and Experimental
TEF	Teaching Excellence Framework

Definitions & Meaning
Faculty Technical Leads	Introduced in April 2020 to have strategic oversight of technical skills across the University; lead on the implementation of the University’s Technician Commitment and represent technical staff at management and University committees where appropriate. Four technical leads (each at 0.2 FTE).
UoS Talent Programme	The purpose of the UoS Talent Plan is to attract, develop, retain, and maintain a diverse and high-performing workforce. Key elements include developing a resourcing plan, employer branding, talent, candidate attraction, new employee pipelines, career advice, and targeted recruitment support to line managers.
Super Recruiter	Trained members of staff who will highlight key ‘touchpoints’ in the recruitment process where inclusion should be considered and advocate for inclusive recruitment practices throughout the process.
Research Culture Landscape Survey	Developed in 2023-2024 by Vitae and piloted with nine HEIs. It gathers views on research culture in UK institutions.
Hub	UoS Technician’s SharePoint page with resources to support technical staff working at the UoS.
Voice of Technicians	Survey of technicians at UoS to gather feedback on work and delivery of TCIG action plan.

Appendix C: Profile of TAE population in the university

Table C1: Number of TAE staff across the university.
Academic Year	Total Staff	TAE Staff	TAE %
2014/15	6309	396	6.3%
2015/16	6386	393	6.2%
2016/17	6605	391	5.9%
2017/18	6418	387	6.0%
2018/19	6270	392	6.3%
2019/20	6184	372	6.0%
2020/21	6011	359	6.0%
2021/22	6009	380	6.3%
2022/23	6296	376	6.0%
2023/24	6761	396	5.9%

Figure C1: TAE Population across university.

Figure C2: Proportion of TAE Employees by Grade.

Figure C3: TAE Employees by Contract Type.

Figure C4: TAE Employees by Gender.

Figure C5: TAE Employees by Ethnicity.

Figure C6: TAE Employees by Disability.